## Slide 1
Monthly Project Health — Executive Synthesis
Portfolio view | Reporting date: 8 July 2026
2 implementation projects assessed: 1 RED, 1 AMBER, 0 GREEN.
Portfolio signal: schedule execution is the dominant risk; budget visibility is insufficient for a complete commercial health view.
Management priority: stabilize delayed work, validate baselines, and close data gaps before the next client governance cycle.

## Slide 2
Portfolio health at a glance
UniSan S2P — AMBER | score 38.4/100 | 42 overdue open tasks | 2 critical overdue.
Titan S2P — RED | score 41.5/100 | 121 severe variance tasks | 3 on hold.
Key divergence: Titan's source plan says Green, but the agent detects material variance and hold signals. This requires PM validation rather than automatic acceptance of the source color.

## Slide 3
Trend 1 — Schedule pressure is systemic
Across both plans, 71 open tasks are past their planned end date.
UniSan has 2 critical overdue tasks, creating near-term milestone exposure.
Titan has 121 tasks with variance of at least 10 days, indicating broader baseline drift.
Executive implication: recovery should focus on critical path and milestone outcomes, not task-count closure alone.

## Slide 4
Trend 2 — Emerging risks and weak signals
Titan comments contain 2 blocker/risk signals and show negative sentiment.
On-hold work and pending dependencies can convert schedule slippage into client-facing milestone misses if ownership is unclear.
Budget burn, forecast-at-completion, and structured stakeholder pulse are absent; commercial and relationship risk remain Unknown.
Data quality itself is a governance signal: missing indicators reduce confidence and can delay escalation.

## Slide 5
Recommended actions — next 30 days
1. Launch a 10-business-day recovery plan for Red work: owner, dependency, committed date, and escalation path.
2. Review all critical overdue items weekly; escalate unresolved external dependencies after 7 days.
3. Validate current dates against the approved baseline; use formal change control for re-baselining.
4. Add weekly budget actuals/EAC and a simple stakeholder pulse (1–5) to the input template.
5. Require PM sign-off when the source-plan color disagrees with the agent's evidence-based status.

## Slide 6
Decisions requested from leadership
Approve focused recovery governance for the Red project and critical overdue work.
Confirm a single portfolio RAG policy so PM-reported colors and automated evidence use the same thresholds.
Mandate minimum weekly data fields: baseline, forecast, actual progress, budget/EAC, blocker owner/age, stakeholder pulse.
Reassess in one week using the same agent to show movement, not just a new snapshot.